## Backlog
Importance | Title | User Story | Estimate
100 | Forms & Input | As a visitor, I would like to input dimensions and select parts for my carport so that I can create the one I want. | 40
100 | Login | As a visitor, I would like to log in so that I can finalize a pre order. | 2
100 | Registration | As a visitor, I would like to sign-up so that I can finalize an order. | 3
100 | Illustration generation | As a logged in customer, I would like to see an illustration of the custom carport I designed after I validated a pre-order, so that I can apply for building permit | 100
100 | Price | As a logged-in customer, I would like to see an approximated price of my carport after I pre-order it so that I can decide to buy it or not | 40
100 | Part list | As an employee, I would like to retrieve a list of parts to use after a customer input dimensions of desired carport, so that I can prepare the delivery | 100
90 | Pre-order | As a logged-in customer, after I designed my custom carport, I would like to pre-order the selected custom carport so that my pre-order is saved in the system | 5
90 | Finalize order & payment | As a logged-in customer, I would like to pay and it can be delivered. | 100
70 | carpenter | As a customer, I would like to receive a list of available carpenters to help me build my carport after I paid for it, so that I can get it built if I can't do it myself (found after Service management interview) | 5
70 | Customer edit personal information | As a logged-in customer, I would like to edit my contact details so that I can be reached and the delivery is at the right address | 3
70 | sales person overview of pre-orders and orders | As a salesperson, I would like to have an overview of all pre-orders and all orders so that I can see if I need to contact customers to push for orders (breakdown needed, sorted by date). | 20
70 | sales person add discount | As a salesperson, I would like to add a discount to an order so that I can convince a customer to buy | 5
50 | Customer edit pre-order | As a logged-in customer, I would like to edit a pre-order so that I can modify my custom carport. | 8
50 | sales person edit pre-orders | As a salesperson, I would like to edit pre-orders so that I can provide better service to customers. | 5
40 | Sales rep. contact details | As a logged-in customer, after a pre-order, I would like to see the contact details of the salespersons assigned to me. | 5
30 | salesperson edit orders | As a salesperson, I would like to edit orders so that I can provide better service to customers. | 5
5 | give priority to orders | As a salesperson, I would like to give a priority factor to an order so that this order is treated first (delivered first). | 8
0 | Check order status | As a logged-in customer, I would like to see the status of my order so that I can check when the carport will be delivered. | 5
0 | updated availability of order notification | As a salesperson, I would like to give a priority factor to an order so that this order is treated first (delivered first). | 40
0 | Delivery estimation | As a visitor, I would like to see the availability of the parts of the custom carport so that I can get an idea of the time it will take to be delivered. | 8
0 | update availability | As a stock employee, I would like to edit availability of a part so that the customer and salesperson have updated information. | 3
0 | affect parts to pre-orders | As an employee responsible of deliveries I would like the system to affect the parts to the pre-orders so that I know what part is for what pre-order | 40
0 | Overview for stock and deliveries | As a stock employee, I would like to see overview of orders so that I can organize my purchase/production of parts and deliveries. | 5

## Backlog filled
Id. | Importance | Title | User Story | Acceptance Criteria | Estimate
2 | 10 | Sorting by likely matches | As a bird finder, I want to see a list of matching birds sorted by likely matches so that I can learn more about bird watching.
1 | 20 | Return list on smartphone | As a bird finder, I want to see a list of matching birds on my smartphone so I can learn more about birds when I’m away from my house.
3 | 30 | Using GPS to find likely matches | As a bird finder, I want to see a list of matching birds based on my uploaded GPS coordinates so that I can learn more about bird watching.