## Backlog
Importance | Title | User Story | Estimate | Acceptance criteria
100 | browse | as a visitor I would like to browse the different custom carports so that I can decide if it the product I desire | 8 | Access the pointy and flat carport pages and see the available dimensions and roof type
100 | Forms & Input | As a logged in customer, I would like to input dimensions and select parts for my carport so that I can create the one I want. | 40 | Access the pointy and flat carport pages and select the available dimensions and roof type
100 | Login | As a visitor, I would like to log in so that I can do an order. | 2 | fill up correctly the fields in login page and being taken to the home page
100 | Registration | As a visitor, I would like to sign-up so that I can do an order. | 3 | inputing information and beingforwarded to the login page where you can then login
100 | Illustration generation | As a logged in customer, I would like to see an illustration of the custom carport I designed after I validated a pre-order, so that I can apply for building permit | 100 | display a basic rectangular shape representing the carport.
100 | Price | As a logged-in customer, I would like to see an approximated price of my carport after I pre-order it so that I can decide to buy it or not | 40 | Able to see the price of a pre-ordered carport in customer overview
100 | Part list | As an employee, I would like to retrieve a list of parts to use after a customer input dimensions of desired carport, so that I can prepare the delivery | 100 | able to see a list of the carport parts
90 | Pre-order | As a logged-in customer, after I designed my custom carport, I would like to pre-order the selected custom carport so that my pre-order is saved in the system | 5 | Click on order and save the order
90 | Finalize order & payment | As a logged-in customer, I would like to pay and it can be delivered. | 100 | pay the order and change the order status
70 | carpenter | As a customer, I would like to receive a list of available carpenters to help me build my carport after I paid for it, so that I can get it built if I can't do it myself (found after Service management interview) | 5 | receive a list of names and phone numbers of carpenters
70 | Customer edit personal information | As a logged-in customer, I would like to edit my contact details so that I can be reached and the delivery is at the right address | 3 | Edit my details and save the changes
70 | sales person overview of pre-orders and orders | As a salesperson, I would like to have an overview of all pre-orders and all orders so that I can see if I need to contact customers to push for orders. | 20 | see a list of all orders and pre-orders
70 | sales person add discount | As a salesperson, I would like to add a discount to an order so that I can convince a customer to buy | 5 | add a discount and update the final price
50 | Customer edit pre-order | As a logged-in customer, I would like to edit a pre-order so that I can modify my custom carport. | 8 | modify a pre-order and save the changes
50 | sales person edit pre-orders | As a salesperson, I would like to edit pre-orders so that I can provide better service to customers. | 5 | modify a pre-order and save the changes
40 | Sales rep. contact details | As a logged-in customer, after a pre-order, I would like to see the contact details of the salespersons assigned to me. | 5 | see the email adress and phone number of the sales person responsible for my order
30 | salesperson edit orders | As a salesperson, I would like to edit orders so that I can provide better service to customers. | 5 | modify an order and save the changes
5 | give priority to orders | As a salesperson, I would like to give a priority factor to an order so that this order is treated first (delivered first). | 8 | change the value of the priority column and change the ordering of the order list
0 | Check order status | As a logged-in customer, I would like to see the status of my order so that I can check when the carport will be delivered. | 5 | see the status of an order
0 | updated availability of order notification | As a salesperson, I would like to give a priority factor to an order so that this order is treated first (delivered first). | 40
0 | Delivery estimation | As a visitor, I would like to see the availability of the parts of the custom carport so that I can get an idea of the time it will take to be delivered. | 8
0 | update availability | As a stock employee, I would like to edit availability of a part so that the customer and salesperson have updated information. | 3
0 | affect parts to pre-orders | As an employee responsible of deliveries I would like the system to affect the parts to the pre-orders so that I know what part is for what pre-order | 40
0 | Overview for stock and deliveries | As a stock employee, I would like to see overview of orders so that I can organize my purchase/production of parts and deliveries. | 5

## Backlog filled
Id. | Importance | Title | User Story | Acceptance Criteria | Estimate
2 | 10 | Sorting by likely matches | As a bird finder, I want to see a list of matching birds sorted by likely matches so that I can learn more about bird watching.
1 | 20 | Return list on smartphone | As a bird finder, I want to see a list of matching birds on my smartphone so I can learn more about birds when I’m away from my house.
3 | 30 | Using GPS to find likely matches | As a bird finder, I want to see a list of matching birds based on my uploaded GPS coordinates so that I can learn more about bird watching.